DAVE

Sprint 3 Iteration Plan

[Note: Text enclosed in square brackets and displayed in blue italics (style=InfoBlue) is included to provide guidance to the author and should be deleted before publishing the document.]

# 1. Key milestones

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| Iteration start | 05.10.2017 |
| Render Messages from JSON | 17.10.2017 |
| Render System Box from JSON | 17.10.2017 |
| Parse JSON | 15.10.2017 |
| Communication Protocol | 15.10.2017 |
| Iteration stop | 19.10.2017 |

# 2. High-level objectives

* Requirements
* Quality Attribute Scenarios
* Render Parallelism

# 3. Work Item assignments

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Name or key words of description** | **Priority** | **Velocity estimate** | **State** | **Reference material** | **Target iteration** | **Assigned to** | **Hours worked** | **Estimate of hours remaining** |
| Vision  ID: 5 | Must | 4 | Done | [Product Backlog](https://trello.com/b/8ugO9kQY) | Sprint 2  (Late) | Elaine | 1 | None |
| Lifeline Animations  ID: 12 | Must | 9 | Done | [Product Backlog](https://trello.com/b/8ugO9kQY) | Sprint 2  (Rework feedback) | Shaun | 4 | None |
| Message Animations  ID: 13 | Must | 8 | 95% done | [Product Backlog](https://trello.com/b/8ugO9kQY) | Sprint 2 | Shaun | 5 | 1 |
| Activation Box Animation  ID: 14 | Must | 11 | Done | [Product Backlog](https://trello.com/b/8ugO9kQY) | Sprint 2 (Rework feedback) | Shaun | 2 | None |
| Communication Protocol  ID: 17 | Must | 11 | 50% done | [Product Backlog](https://trello.com/b/8ugO9kQY) | Sprint 3 | Elaine | 30 | N/A |
| Parse JSON  ID: 18 | Must | 9 | Done | [Product Backlog](https://trello.com/b/8ugO9kQY) | Sprint 3 | Erik | 21 | None |
| Render System Box from JSON  ID: 19 | Must | 13 | Done | [Product Backlog](https://trello.com/b/8ugO9kQY) | Sprint 3 | Boyan | 18 | None |
| Camera Movement Controls  ID: 20 | Must | 10 | Done | [Product Backlog](https://trello.com/b/8ugO9kQY) | Sprint 2  (Rework feedback) | Justinas | 4 | None |
| Render Messages from JSON  ID: 21 | Must | 13 | Done | [Product Backlog](https://trello.com/b/8ugO9kQY) | Sprint 3 | Joacim | 14 | None |
| Render Parallelism  ID: 22 | Must | 14 | 90% | [Product Backlog](https://trello.com/b/8ugO9kQY) | Sprint 3 | Justinas | 25 | 5 |

# 4. Issues

|  |  |  |
| --- | --- | --- |
| **Issue** | **Status** | **Notes** |
| Missing an agenda | Attempting to fix | Meetings with result in a lower efficiency if no agenda was set before hand |
| Members being late | N/A | Several members overslept (accidentally) and ended up being late. |
| Members missing meetings | Solved | Several members were sick therefore could not attend meetings |
| Failing to follow process | Attempting to fix | Members did not update Trello or GitHub. The members were reminded to update their progress. |
| Confusion around user stories | Attempting to fix | Confusion surrounding task and their scopes was identified. In the future will attempt to solve through diagram visualization |

# 5. Evaluation criteria

## Milestones met

## High Level Objectives met

## Pull Requests approved by 2 people

## Product owner approval

# 6. Assessment

|  |  |
| --- | --- |
| Assessment target | All |
| Assessment date | 19.10.2017 |
| Participants | Michael Palka, Mayra Soliz, Emanuel Marcos, Boyan Dai, Erik Laurin, Elaine Qvarnström, Joacim Eberlen,  Justinas Stirbys, Shaun McMurray |
| Project status | Behind |

## Assessment against objectives

Communication protocol failed to meet the due date. Animations tasks were completed but not integrated on time.

## Work Items: Planned compared to completed

Render Parallelism failed to meet due date

## Assessment against Evaluation Criteria Test results

Camera Movement Controls was only approved by 1 person before merging.

## Other concerns and deviations

None